## SEO Checklist
Task ID | SEO Task | Category | Priority | Status | Assigned To | Due Date | Notes
1 | Conduct keyword research | Keyword Strategy | High | Not Started | SEO Intern | 15-Sep-2025 | Focus on fashion-related keywords
2 | Map keywords to product & blog pages | Keyword Strategy | High | Not Started | SEO Intern | 16-Sep-2025 | Use long-tail + LSI keywords
3 | Optimize meta titles & descriptions | On-page SEO | High | In Progress | SEO Manager | 20-Sep-2025 | Add primary keywords
4 | Add alt text to images | On-page SEO | Medium | Not Started | Content Team | 22-Sep-2025 | Use keyword-rich descriptions
5 | Submit XML sitemap to Google | Technical SEO | High | Not Started | Developer | 30-Sep-2025 | Verify indexing in GSC